## Sensitivity Report 1
Microsoft Excel 7.0a Sensitivity Report
Changing Cells
|  |  | Final | Reduced
| Cell | Name | Value | Gradient
| $B$6 | Start Time | 0 | 1
| $B$7 | Start Time | 12 | 0
| $B$8 | Start Time | 20 | 0
| $B$9 | Start Time | 20 | 0
| $B$10 | Start Time | 24 | 0
| $B$11 | Start Time | 32 | 0
| $B$12 | Start Time | 36 | 0
Constraints
|  |  | Final | Lagrange
| Cell | Name | Value | Multiplier
| $F$6 | Time | 12 | 1
| $F$7 | Time | 8 | 1
| $F$8 | Time | 8 | 0
| $F$9 | Time | 0 | 1
| $F$10 | Time | 4 | 0
| $F$11 | Time | 12 | 1
| $F$12 | Time | 8 | 0
| $F$13 | weeks Time | 4 | 1

## Answer Report 1
Microsoft Excel 7.0a Answer Report
Target Cell (Min)
| Cell | Name | Original Value | Final Value
| $B$13 | Project time = Start Time | 36 | 36
Adjustable Cells
| Cell | Name | Original Value | Final Value
| $B$6 | Start Time | 0 | 0
| $B$7 | Start Time | 12 | 12
| $B$8 | Start Time | 20 | 20
| $B$9 | Start Time | 20 | 20
| $B$10 | Start Time | 24 | 24
| $B$11 | Start Time | 32 | 32
| $B$12 | Start Time | 36 | 36
Constraints
| Cell | Name | Cell Value | Formula | Status | Slack
| $F$6 | Time | 12 | $F$6>=$G$6 | Binding | 0
| $F$7 | Time | 8 | $F$7>=$G$7 | Binding | 0
| $F$8 | Time | 8 | $F$8>=$G$8 | Not Binding | 4
| $F$9 | Time | 0 | $F$9>=$G$9 | Binding | 0
| $F$10 | Time | 4 | $F$10>=$G$10 | Binding | 0
| $F$11 | Time | 12 | $F$11>=$G$11 | Binding | 0
| $F$12 | Time | 8 | $F$12>=$G$12 | Not Binding | 4
| $F$13 | weeks Time | 4 | $F$13>=$G$13 | Binding | 0
| $B$6 | Start Time | 0 | $B$6>=0 | Binding | 0
| $B$7 | Start Time | 12 | $B$7>=0 | Not Binding | 12
| $B$8 | Start Time | 20 | $B$8>=0 | Not Binding | 20
| $B$9 | Start Time | 20 | $B$9>=0 | Not Binding | 20
| $B$10 | Start Time | 24 | $B$10>=0 | Not Binding | 24
| $B$11 | Start Time | 32 | $B$11>=0 | Not Binding | 32
| $B$12 | Start Time | 36 | $B$12>=0 | Not Binding | 36

## Sensitivity Report 2
Microsoft Excel 7.0a Sensitivity Report
Changing Cells
|  |  | Final | Reduced | Objective | Allowable | Allowable
| Cell | Name | Value | Cost | Coefficient | Increase | Decrease
| $B$6 | Start Time | 0 | 1 | 0 | 1e+30 | 1
| $B$7 | Start Time | 12 | 0 | 0 | 1e+30 | 1
| $B$8 | Start Time | 20 | 0 | 0 | 1e+30 | 1
| $B$9 | Start Time | 20 | 0 | 0 | 1e+30 | 1
| $B$10 | Start Time | 28 | 0 | 0 | 0 | 1
| $B$11 | Start Time | 32 | 0 | 0 | 1e+30 | 1
| $B$12 | Start Time | 36 | 0 | 1 | 1e+30 | 1
Constraints
|  |  | Final | Shadow | Constraint | Allowable | Allowable
| Cell | Name | Value | Price | R.H. Side | Increase | Decrease
| $F$6 | Time | 12 | 1 | 12 | 1e+30 | 12
| $F$7 | Time | 8 | 1 | 8 | 1e+30 | 4
| $F$8 | Time | 8 | 0 | 4 | 4 | 1e+30
| $F$9 | Time | 0 | 1 | 0 | 1e+30 | 4
| $F$10 | Time | 8 | 0 | 4 | 4 | 1e+30
| $F$11 | Time | 12 | 1 | 12 | 1e+30 | 4
| $F$12 | Time | 4 | 0 | 4 | 4 | 1e+30
| $F$13 | weeks Time | 4 | 1 | 4 | 1e+30 | 36

## Sheet1
House Building Project
[5 empty] | Actual | Network | Activity | Activity | Actual
| Earliest |  | Activity |  | Activity | Activity | Crash | Crash | Crash
Node | Event Time |  | Node | Node | Time | Time | Cost | Time | Time
1 |  |  | 1 | 2 | 0 | 12 | 400 | 5 | 0
2 |  |  | 2 | 3 | 0 | 8 | 500 | 3 | 0
3 |  |  | 2 | 4 | 0 | 4 | 3000 | 1 | 0
4 |  |  | 3 | 4 | 0 | 0 | 0 | 0 | 0
5 |  |  | 4 | 5 | 0 | 4 | 200 | 3 | 0
6 |  |  | 4 | 6 | 0 | 12 | 7000 | 3 | 0
7 |  |  | 5 | 6 | 0 | 4 | 200 | 3 | 0
Project time = | 0 | weeks | 6 | 7 | 0 | 4 | 7000 | 1 | 0
Project goal = | 30 | weeks
Project cost = | 0 | dollars